Alicia

Technology Proposal: 3-Dimentsional Printers

Introduction

This proposal asserts and defends the proposition that three 3D printers be bought for the school. These printers would allow students and staff to design and create their own three-dimensional objects, shapes, and models. In the plan that is outlined in this proposal, one printer will be given to fifth grade and one to fourth, leaving the last one for the lower grades. These printers will impact students’ success in many ways, including creating engaging opportunities for learning, use of modern technology, and building of collaborative skills, but the focus will be on how it can help students deepen their understanding of mathematics. The printers would be bought through the Maker’s Empire. The cost for the three printers, including tax, shipping, online training, and 5,000 grams of PLA filament is $4,399.00. Additionally, the teachers would have to be paid during the training, which would add $1,800 to the initial cost. There should be no installation cost. This proposal will outline the expected benefits and outcomes that the printers will bring is worth the initial investment.

Benefits of the Technology

In a fast-paced, technologically advancing world, the 3D printer will engage students to build and strengthen many different skills. These skills include creating physical models of geographic, scientific, and mathematical concepts. For example, students could build a model showing the layers of the earth. That project, and many like it, would introduce the content in a way that requires critical thinking skills. The printers will also stretch collaboration skills, as many projects are best done in a group. They will stretch creativity and divergent thinking. They will allow students to experiment with modern equipment that is used in professional fields. These are only some of the benefits of implementing this technology will bring. Any single one of these listed aspects could be expanded on as a critical reason to introduce 3D printers to the classroom, but this proposal will focus on the mathematical outcomes.

Impact on Classroom Instruction

Many students struggle mathematically. In the 2017 Minnesota Comprehensive Assessment (MCA), in 2017 31.4% of fourth grade students did not meet the math standards requirements. In 2018, 44.5% of those same students did not meet the standards. This shows that math instruction in younger grades is not supporting the transition as students step into older grades. This is supported by showing that by 11th grade, over half the students test did not reach the standards (Minnesota Department of Education, 2018). There is a problem with providing proper supports as students learn more difficult math.

One transition that is especially difficult for students is going from upper elementary math to middle school. Whitney (2015) claims that most students lose interest in math between the ages of 9-14. Nine is right at fourth grade. Boling (1991) echoes this, saying that after fourth grade, in each progressive grade students are more likely to claim math as their least favorite subject. This is supported by the data shown in the MCA results compiled by the Minnesota report card. These two authors claim the decline in mathematics at this age is partially due to the content becoming more and more abstract. At this point, teaching math through paper can be difficult and unsuccessful. Three-dimensional printers are one tool that would make mathematics more concrete, practical, and engaging for the students. Especially relating to fourth and fifth grade Minnesota math standards, 3D printers are a tool for laying a foundation to aid students as they approach more abstract math.

Figure 1: Credit Easy as Pie Fractions by ThreeDeePrint.

Three-dimensional printers are especially well-fitted to creating a concrete foundation for geometry and fractions. For example, take fourth-grade Minnesota mathematical 4.1.2.3, asking students to “use fraction models to add and subtract fractions with like denominators in real-world and mathematical situations.” Note the word models and real-world. Kane (2017) writes about a teacher who has his students create models of fractions using 3D printers (see figure 1).  These modeling blocks are created so that students can use them to physically add and subtract fractions. Seeing this in such a physical way helps students to understand the concrete reasons behind the math that will help them to gain a strong foundational understanding of fractions. This not only helps students in their initial understanding of fractions, but it will lay a foundation as fractions become more and more abstract in Algebra.

Another direct standard that would be effected by a 3D printer is the Minnesota Math Standard 5.3.2.3, “Represent real-world situations using equations and inequalities involving variables. Create real-world situations corresponding to equations and inequalities.” The words to note here are represent and real-world. If we want to train students for real world geometry applications, what better way than letting them create real models? Three-dimensional printers allow students to create physical models instead of doing a word problem. For example, students could work as a group to create furnishing for a house. They would be given specific dimensions for some items, but variables could be introduced by allowing students to fill the remaining space independently. This allows for creativity, divergent thinking, collaboration, and development in mathematical skills. It teaches students to use math in ways that it is used in the real world. \

Classroom Use

These are only a few ways that the technology would impact instruction. Almost every lesson in math could be aided by 3D printers and many more subjects could be enriched by it, as well. But the question of how to implement the technology remains. To support students in the transition to abstract math by laying a concrete foundation, three 3D printers should be bought.

Both the fourth and fifth grade teams would be given a printer, leaving one to be shared by the lower grades.

The fifth and fourth grade classes would have the design programs installed on their IPads, so they could plan and build without the printer in the room. The printer would print their designs as they finished their projects. The teachers of the lower grades could do the same thing, reserving the printer when their students were finished designing. This would allow students to learn to use the technology and experience its benefits before working with it more intensely in upper elementary. Most work, especially in younger grades, would be done in groups. This would allow for quicker printing, as well as creating a space for collaboration skills to develop.

The technology would impact all students, but the primary focus would be the fourth and fifth grades. Ideally, as the printers prove that they are an asset, more will be bought, and more students will be impacted.

Outcomes

These printers will bring many positive outcomes, but the one that has been focused on throughout this proposal is developing mathematical skills. Specifically, fourth and fifth graders will strengthen their skills in working with fractions and geometric concepts by equipping both grade levels with a printer.

As previously mentioned, fourth and fifth grade math is a point when students often stop liking math. This is thought to because of the difficulty and abstraction in the curriculum. Furthermore, in a study done by Sung (2015), it showed that students who are taught with multiple, concrete mathematical-representations had better success rates than students who only did traditional worksheets. This is proof that a 3D printer, specifically made for creating accurate representations will help students improve in mathematical concepts that need representation.

To assess this outcome, the school will use both norm and criterion assessments. The school will use summaries of MCA scores in fractional and geometric concepts from the past three years to create a compare to the next three years with the printers. Teachers will also pull any criterion-based assessment records they have to compare with future tests that they give. The scores will be assessed for comparison. Further testing will be recorded as necessary. Teachers will also record anecdotal notes and impressions of student engagement and learning caused by the printers. This compiled data will show whether the outcome has been reached.

A corresponding outcome is that fourth and fifth grader attitudes towards these concepts will become more positive. This is because they will be taught in a real-life, applicable, engaging, concrete way that enhances student understanding. These contradict the abstract confusion that turns many students off to math.

This outcome will be assessed through student and teacher surveys. The students who were the last to go to middle school without the 3D printers will be given a survey to show their views towards the mathematical concepts. These will be compared with the incoming fourth and fifth graders who will also be given surveys before and after their year of working with the printers. This will assess their attitude towards geometric and fractional concepts in mathematics before and after their year. It will also assess their views towards the technology. The incoming fourth graders will also complete a similar survey after they finish their second year with the printers. These surveys will assess the students’ views on their understanding, engagement, and attitudes towards math concepts and technology.

The compilation of this data will show whether the 3D printers successfully met the outcome goals. They will also help school personal to evaluate the possibility and potential and value of bringing in more 3D printers.

Potential Challenges

The printers are expected to enhance learning, but they will not be without challenges. The first challenge will be training the teachers to use these tools successfully. Without proper training, teachers will not be able to successfully implement these into their classrooms. That is why the purposed purchase packet includes online training and support. Teachers would be required to complete the online training before implementing the printer into their curriculum. This will have to be a paid training which would add another eighteen hundred to the initial cost.

Similarly, teachers will face the challenge of teaching their student how to use the equipment properly and respectfully. This will take time, but the longer the technology exists in the school, the easier this will become.

Another challenge would be dividing time with the printer up with the classroom. This is something that individual teams would need to consult on. Each class can design and build without the printer in the room, so the teams would need to decide how to share printing time. Time will be given to each grade level team to discuss the use of their printer during training.

Finally, this technology would need to be maintained. When the PLA filament is used, it will need to be rebought, just like printer paper. For three printers, this will be an annual cost of about $250.00. However, all of these challenges do not negate the value of what the technology could do for the classroom.

Item Expense

There are many different 3D printers to choose from, but Maker’s Empire offers a package that would supply all the needs for the first year of implementation.

| ITEM | COST |
| --- | --- |
| Makers Empire Maker Package | $4,399 |
| Makers Empire School Subscription |  |
| 3 H400 3D printers |  |
| 10 500g rolls of biodegradable PLA filament |  |
| Online hardware training and support |  |
| Training teacher (30) (60) (# of employees) (wage x 3) | $1,800 |
| Total: | $6,199 |

Source of the cost information: https://www.makersempire.com/the-best-3d-printer-for-your-school-2018-usa/

Summary

Implementing this technology would give teachers a resource to allow students, especially fifth and fourth graders, to create models that would engage them in many subjects. It is especially suited for making math concepts like geometry and fractions concrete and practical. Students would gain deeper understanding of afore mentioned concepts, have better attitudes towards math as they enter middle school, and build other fundamental skills. Most challenges would be overcome with training and discussion. The initial cost of the item includes all the tools needed for successful implementation, and is well worth it for the benefits that would be reaped from the new technology.

References

Boling, A. N. (1991). They don't like math? well, let's do something! The Arithmetic Teacher,

38(7), 17. Retrieved from http://ezproxy.unwsp.edu/login?url=https://search-proquest-com.ezproxy.unwsp.edu/docview/208774074?accountid=12915

Kane, K. (2017, Feb 24). 9 amazing ways teachers can use 3D printing to teach math and

science. Retrieved from https://www.weareteachers.com/3d-printing-math-science/

Kalbitzer, S., & Loong, E. (2013). Teaching 3-D Geometry - the multi representational way.

Australian Primary Mathematics Classroom, 18(3), 23–28. Retrieved from https://login.ezproxy.unwsp.edu/login?url=https://search.ebscohost.com/login.aspx?direct=true&db=keh&AN=99013411&site=ehost-live&scope=site

Makers Empire (2018) The best 3D printer for your school. Makers Empire. Retrieved from

https://www.makersempire.com/the-best-3d-printer-for-your-school-2018-usa/

Minnesota Department of Education (2018) Mineesota report card: MCA/MTA’s. Retrieved

from https://rc.education.state.mn.us/#MCAMTAS/orgId--999999000000__groupType--state__test--allAccount__accountabilityFlg--Y__subject--M__grade--03__p--1d

Sung, Y., Shih, P., & Chang, K. (2015). The effects of 3D-representation instruction on

composite-solid surface-area learning for elementary school students.Instructional

Science, 43(1), 115-145. doi:http://dx.doi.org.ezproxy.unwsp.edu/10.1007/s11251-014-9331-8

Whitney, A. K. (2015, Aug 4) Why did I give up on math? The Washington Post. Retrieved from

https://www.washingtonpost.com/posteverything/wp/2015/08/04/why-did-i-give-up-on-math-ask-my-mom/?utm_term=.124e8f274b21